## Volcanoes
Volcanoes Statement of Work
| Project Title |  | Start Date
| Events |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Ausar (SWE), Ja'Nya (Lead), Jon (Designer), no Tester |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments | Status
| Ausar |  |  | 2025-11-18 | 2025-12-08 | 21 |  | Not Started
| #31 Create Alert class | Complete | SHA 61e722a | 2025-11-18 | 2025-11-18 | 1 |  | In Progress
| Created FeedService Class | Complete | SHA 9886a0b | 2025-11-24 | 2025-11-30 | 6 |  | Complete
| Created NotificationService Class | Complete | SHA 9886a0b | 2025-11-24 | 2025-11-30 | 6 |  | On Hold
| Integrated Services into Event Cancellation Workflow | Complete | SHA c0edce3 | 2025-11-24 | 2025-11-30 | 6
| Add unit tests for FeedService, EventCancellationService, CalendarSyncService | Complete | SHA dd1fe1a | 2025-11-24 | 2025-11-30 | 6
| Event Cancellation System (: Xavier University Event Cancellation System,Add EventCancellationManager with cancel and undo functionality,: Add Event Cancellation Manager with undo functionality) | Complete | SHA c552fd97 ,95c802f2, f29d357e | 2025-11-24 | 2025-11-30 | 6
| User Story #8: Alert Subscription System | Complete | SHA a6c76ff7,1a3dce8d,857c864c | 2025-11-24 | 2025-11-30 | 6
Nov 26th: 8 commits, +4906, -8
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Ja'Nya |  |  | 2025-11-10 | 2025-12-08 | 29
| # Update README with prioritized projects | On Hold | SHA 1fc9902 | 2025-11-10 | 2025-11-10 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint.
Nov 26th: 28 commits, +393, -38
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Jon |  |  | 2025-11-18 | 2025-12-08 | 21
| # Create CPSC_event class | On Hold | SHA 52b08c9 | 2025-11-18 | 2025-11-18 | 1 | What is this use case's user story number? If no user story, make sure you add this as a user story in our final sprint. | You and Ja'Nya need to figure out why Ausar is listed as a contributor to our shared repo but you are not. You can't earn points for this assignment unless you are a contributor.
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Vacant |  |  | 0 | 0 | 0
Nov 26th: 30 commits, +461, -122
Formulas:
Start Date = MIN([Start Date, row below]:F21)
End Date = MAX([End Date, row below]:G21)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL