## Volcanoes
Volcanoes Statement of Work
| Project Title |  | Start Date
| Events |  | 2025-11-09 |  |  | Project Duration
| Project Development Team |  | End Date |  |  | in days
| Ausar (SWE), Ja'Nya (Lead), Jon (Designer), no Tester |  | 2025-12-01 |  |  | 23
| User Story # | Status | Use Cases | Start Date | End Date | Duration (in days) | Comments
| Ausar |  |  | 2025-11-18 | 2025-12-08 | 21
Alert (__init__, __repr__, send_alert, update_preferences) | #31 Create Alert class | Complete | SHA 61e722a | 2025-11-18 | 2025-11-18 | 1
FoodService( __init__, add_event, remove_event) NotificationService (notify_followers) | Created FeedService Class, Created NotificationService Class | Complete | SHA 9886a0b | 2025-11-24 | 2025-11-30 | 6
cancel_event | Integrated Services into Event Cancellation Workflow | Complete | SHA c0edce3 | 2025-11-24 | 2025-11-30 | 6
test_generate_ics_canceled_event, test_generate_ics_active_event, test_sync_to_all_integrations, test_sync_to_specific_integration, test_sync_history_tracking Tests_EventCancellationService | Add unit tests for FeedService, EventCancellationService, CalendarSyncService | Complete | SHA dd1fe1a | 2025-11-24 | 2025-11-30 | 6
edited README, edited main CancellationError EventCancellationManager | Event Cancellation System (: Xavier University Event Cancellation System,Add EventCancellationManager with cancel and undo functionality,: Add Event Cancellation Manager with undo functionality) | Complete | SHA c552fd97 ,95c802f2, f29d357e | 2025-11-24 | 2025-11-30 | 6
reworked Alert User edited README with generated other docs | User Story #8: Alert Subscription System | Complete | SHA a6c76ff7,1a3dce8d,857c864c | 2025-11-24 | 2025-11-30 | 6
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Ja'Nya |  |  | 2025-11-10 | 2025-12-08 | 29
README | Update README with prioritized projects | Complete | SHA 1fc9902 | 2025-11-10 | 2025-11-10 | 1
check_conflict(), register_event(), TestConflicChecker, test_register_event_adds_Event | User Story #2 | Complete | SHA 8325caa, 4d0650f, 86667ee, a62f2e5, 9bae98a | 2025-11-25 | 2025-11-30 | 6
get_rsvp_users_for_event, RSVP (__init, __repr__), get_users_object_for_event, | User Story #32 | Complete | SHA 4b7384b, 1601710, 9c96ccc, 3f0d0c4, 763b2f6, 1a7dce3, acddb02, ae78e72, 194f939 | 2025-11-30 | 2025-12-01 | 2
is_event_virtual, __repr__ | User Story #35 | Complete | a8e840c, d422f79, | 2025-11-19 | 2025-11-19 | 1
Events( __init__, create_event) FilterEvent(__init__) | User Story #33 | Complete | 62c36dd, aaeb490, ac06a4f, | 2025-11-18 | 2025-11-18 | 1
validate_event_time, update_event_time | User Story #6 | Complete | bfa6b1f, 72bf603 | 2025-11-18 | 2025-11-25 | 8
RSVP_Service (__init__, create_rsvp, cancel_rsvp, __repr__, get_usr_rsvps) | User Story #37 | Complete | d56cae5, 7a06c99, 22433d, 9451f75, b3484fa, 54a2ec7, | 2025-11-25 | 2025-11-25 | 1
| Evaluate Dr. Edwards via Class Climate | Complete |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
| Jon |  |  | 2025-11-18 | 2025-12-08 | 21
| # Create CPSC_event class | On Hold | SHA 52b08c9 | 2025-11-18 | 2025-11-18 | 1 | Jon earned a zero for Assignment08 because he didn't submit his SOW. If I'm in error, Jon should email me a SHA with his Excel spreadsheet.
| Evaluate Dr. Edwards via Class Climate | Not Started |  | 2025-11-22 | 2025-12-08 | 17
| Evaluate team using Brightspace survey | Not Started |  | 2025-12-01 | 2025-12-01 | 1
Formulas:
Start Date = MIN([Start Date, row below]:F16)
End Date = MAX([End Date, row below]:G16)

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.
https://www.smartsheet.com/top-project-management-excel-templates?srsltid=AfmBOorM8KTqo0GkEazFKhVFp3ozfOh-BifeI1KKxQxM0WpR5p08gBRL